## Workplan
High Road Training Partnership: Resilient Workforce Program (RWP)
Work Plan
Organization | Equitable Food Initiative
Project Name | High Road to Better Agricultural Jobs
Objectives/Activities |  | Estimated Completion Dates
Quarter 1
Facilitate a convening (likely in Sacramento) of at least 30 representatives of employer and worker organizations, training providers, community colleges, experts and relevant state agencies (including CWDB, CDFA, LWDA) to refine a draft framework for a credentialing process, and to formalize an ongoing steering committee for the network. |  | 2024-09-27
Engage prospective high road employers in the EFI certification process through site visits, worker-manager training and support to audit planning. |  | 2024-09-27
Quarter 2 |  | Estimated Completion Dates
Facilitate bi-monthly steering committee meetings to refine and approve draft work plan and credentialing roadmap prepared by EFI and JFF based on stakeholder input from the convening; determine which skills from the evolving catalogue will be prioritized for pilot training; create standardized curriculum for specific frontline agricultural roles; and begin funding proposal development for pilot training. |  | 2024-12-20
Continue to engage prospective high road employers in the EFI certification process through site visits, worker-manager training and support to audit planning. |  | 2024-12-20
Deliver at least two introductory trainings on sustainability and climate mitigation strategies to worker-manager teams on certified farms. Finalize methodology and begin to market a training package beyond EFI-certified farms to the broader California agricultural community. |  | 2024-12-20
Quarter 3 |  | Estimated Completion Dates
Consolidate steering committee focus on priority skills curriculum for frontline workers and supervisors and begin planning for pilot sites and processes; submit proposals to fund 2025 pilot training. |  | 2025-03-28
Continue to engage prospective high road employers in the EFI certification process through site visits, worker-manager training and support to audit planning. |  | 2025-03-28
Deliver first grower-funded climate and sustainability trainings |  | 2025-03-28
Quarter 4 |  | Estimated Completion Dates
Steering committee finalizes 2025-26 roadmap to formalizing agricultural skill credentials, schedule for 2025 pilot trainings by region and commodity, and grant agreements for pilot funding. |  | 2025-06-27
High Road growers in California plan to integrate skills training |  | 2025-06-27
EFI expands marketing and delivery of climate training. |  | 2025-06-27
Quarter 5 |  | Estimated Completion Dates
Quarter 6 |  | Estimated Completion Dates
Quarter 7 |  | Estimated Completion Dates
Quarter 8 |  | Estimated Completion Dates
Quarter 9 |  | Estimated Completion Dates
Quarter 10 |  | Estimated Completion Dates
Quarter 11 |  | Estimated Completion Dates
Quarter 12 |  | Estimated Completion Dates
Quarter 13 |  | Estimated Completion Dates