## Workplan
High Road Training Partnership: Resilient Workforce Program (RWP)
Work Plan
Organization | JEWISH VOCATIONAL AND CAREER COUNSELING SERVICE
Project Name | Delivering Automotive Pre-Apprenticeship Training Programs in the Bay Area
Objectives/Activities |  | Estimated Completion Dates
Quarter 1
Convene core partners to discuss grant and objectives |  | 2024-07-31
establish regular meeting cadence |  | 2024-07-31
Quarter 2 |  | Estimated Completion Dates
draft MOUs |  | 2024-10-31
engage core partners in program planning |  | 2024-12-31
introduce job quality framework |  | 2024-12-31
Quarter 3 |  | Estimated Completion Dates
MOUs signed by all parties |  | 2024-03-31
identify training partner for math portion |  | 2024-03-31
identify other employer partners to collaborate with |  | 2024-03-31
Quarter 4 |  | Estimated Completion Dates
draft MOUs for new partners |  | 2025-04-30
convene partners to plan program launch |  | 2025-04-30
get MOUs signed by new partners |  | 2025-06-30
one employer uses job quality framework to assess open roles |  | 2025-06-30
Quarter 5 |  | Estimated Completion Dates
Quarter 6 |  | Estimated Completion Dates
Quarter 7 |  | Estimated Completion Dates
Quarter 8 |  | Estimated Completion Dates
Quarter 9 |  | Estimated Completion Dates
Quarter 10 |  | Estimated Completion Dates
Quarter 11 |  | Estimated Completion Dates
Quarter 12 |  | Estimated Completion Dates
Quarter 13 |  | Estimated Completion Dates