## Workplan
High Road Training Partnership: Resilient Workforce Program (RWP)
Work Plan
Organization | United Auto Workers
Project Name | Center for Manufacturing a Green Economy
Objectives/Activities
Quarter 1 |  | Estimated Completion Dates
Convene first Labor/Management oversight committee meeting |  | 2024-07-01
Establishment of formal MOU between Labor and Management |  | 2024-07-20
Convene two more Labor/Management oversight committee meetings |  | 2024-09-27
Establish goals and objectives for the workforce development planning process and obtain approval from the Labor/Management oversight committee |  | 2024-08-15
Identify curriculum preparation team including labor educators, technical specialists and management representatives. Will be an ongoing process over six months. |  | 2024-09-27
Identify a local Sacramento resident with knowledge of community-based organizations to join the staff as the Program Manager |  | 2024-08-15
Identify initial potential educational partners and curriculum developers and conduct first meeting to develop plan |  | 2024-08-15
Obtain a detailed list of job titles and descriptions for the new facility and develop list required skills. |  | 2024-08-01
Contract with educational partners for participation on the curriculum development team. Will be an ongoing process over six months. |  | 2024-09-27
Prepare a database system to track outcomes, deliverables, and expenditures |  | 2024-08-15
Quarter 2 |  | Estimated Completion Dates
Develop basic skills curriculum with educational team |  | 2024-10-01
Develop on the job skills attainment curriculum |  | 2024-10-01
Develop coaching and mentoring program - curriculum to train new coaches and mentors |  | 2024-10-01
Meet with potential recruitment partners and begin to develop detailed recruitment plan to reach target populations |  | 2024-10-01
Develop health and safety training modules |  | 2024-10-01
Convene Labor/Management committee monthly for continued oversight of the program - at each meeting share progress towards outcomes as tracked in the database. |  | 2024-12-23
Quarter 3 |  | Estimated Completion Dates
Present draft basic skills, on-the-job skills and health and safety curricula to Labor/Management oversight committee. |  | 2025-02-01
Make adjustments to the curricula based on feedback from the Labor/Management committee |  | 2025-03-31
Develop outreach materials for Recruitment partners and schedule meetings to review and plan for presentations |  | 2025-01-01
Make adjustments to outreach materials and print materials, finalize slide shows, and schedule presentations. |  | 2025-02-01
Quarter 4 |  | Estimated Completion Dates
Conduct outreach and recruitment sessions with community-based organizations and SETA. |  | 2025-05-01
Present to Labor/Management committee the final training curriculum documents and recommendations for selection of candidates and training schedule. |  | 2025-06-30
Quarter 5 |  | Estimated Completion Dates
Quarter 6 |  | Estimated Completion Dates
Quarter 7 |  | Estimated Completion Dates
Quarter 8 |  | Estimated Completion Dates
Quarter 9 |  | Estimated Completion Dates
Quarter 10 |  | Estimated Completion Dates
Quarter 11 |  | Estimated Completion Dates
Quarter 12 |  | Estimated Completion Dates
Quarter 13 |  | Estimated Completion Dates