## Workplan
High Road Training Partnership: Resilient Workforce Program (RWP)
Work Plan
Organization | Western States Council of Sheet Metal Workers
Project Name | High Road to Sheet Metal: WSC-SMART
Objectives/Activities |  | Estimated Completion Dates
Quarter 1
5th Year apprentices graduate. A new cohort enters apprenticeship. UC Davis WCEC begins making recommendations on training equipment for JATCs. High Road Outreach Staff is hired and trained by Lead Business Development staff with experience in outreach to l Advertising and outreach materials will begin to be created and utilized through digital and traditional (radio) for JATCs with little-to-no backlog; San Diego JATC website; Nipomo advertising, Modesto Advertising Quarterly HRTP Convening |  | 2024-09-30
Quarter 2 |  | Estimated Completion Dates
JATCs continue to receive recommendations from WCEC, purchase equipment, and install using apprentice on-the-job training. Limited # of apprentices/journeypersons take upgrade courses. High Road Outreach Staff deployed in high-need areas to gain market share. Quarterly HRTP Convening |  | 2024-12-31
Quarter 3 |  | Estimated Completion Dates
JATCs continue to receive recommendations from WCEC, purchase equipment, and install using apprentice on-the-job training. Quarterly HRTP Convening High Road Outreach Staff deployed in high-need areas to gain market share. |  | 2025-03-31
Quarter 4 |  | Estimated Completion Dates
JATCs continue to receive recommendations from WCEC, purchase equipment, and install using apprentice on-the-job training. Apprentices/journeymen continue training. High Road Outreach Staff deployed in high-need areas to gain market share. Quarterly HRTP Convening |  | 2025-06-30
Quarter 5 |  | Estimated Completion Dates
5th Year apprentices graduate. A new cohort enters apprenticeship. All equipment is installed, apprentices receive training, and journeypersons take upgrade classes on new equipment. Apprentices/journeymen continue training. High Road Outreach Staff deployed in high-need areas to gain market share. Quarterly HRTP Convening, with more in-depth discussion discussing first-year progress and the coming year. |  | 2025-09-30
Quarter 6 |  | Estimated Completion Dates
All equipment is installed, apprentices receive training and journeymen take upgrade classes on new equipment/skills. Apprentices/journeymen continue training. High Road Outreach Staff deployed in high-need areas to gain market share Quarterly HRTP Convening |  | 2025-12-31
Quarter 7 |  | Estimated Completion Dates
All equipment is installed, apprentices receive training and journeymen take upgrade classes on new equipment/skills. High Road Outreach Staff deployed in high-need areas to gain market share. Quarterly HRTP Convening |  | 2026-03-31
Quarter 8 |  | Estimated Completion Dates
Quarter 9 |  | Estimated Completion Dates
Quarter 10 |  | Estimated Completion Dates
Quarter 11 |  | Estimated Completion Dates
Quarter 12 |  | Estimated Completion Dates
Quarter 13 |  | Estimated Completion Dates